## Sheet1
Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
| 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-09-27 | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22
Finalization | bar: 2026-09-06 to 2026-09-13
GitHub Setup | bar: 2026-09-06 to 2026-09-13
Survey Design & Ethics Approval | bar: 2026-09-13 to 2026-09-27
Survey Distribution & Analysis | bar: 2026-09-27 to 2026-10-11
Design | bar: 2026-10-04 to 2026-10-18
Requirements | bar: 2026-10-11 to 2026-11-01
Early Prototype | bar: 2026-10-18 to 2026-11-08
Review, Corrections & Submission | bar: 2026-11-08 to 2026-11-22
Milestones | 2026-09-06: ◆ M1; 2026-09-20: ◆ M2; 2026-10-04: ◆ M3; 2026-10-18: ◆ M4; 2026-11-01: ◆ M5; 2026-11-15: ◆ M6

## Sheet2
Milestone | Expected Output
M1 | Finalization and GitHub setup completed
M2 | Survey design and ethics approval completed
M3 | Survey distribution and analysis completed
M4 | System design completed
M5 | Requirements and early prototype completed
M6 | Final review, corrections, and project submission completed